## Gantt Chart
BrightTV Project · Gantt Chart
# | Task Name | Start Date | End Date | Duration
[5 empty] | Tue 08 | Wed 09 | Thu 10 | Fri 11 | Sat 12 | Sun 13 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Sat 19 | Sun 20 | Mon 21 | Tue 22
1 | Data Inspection | 08-Apr | 09-Apr | 1 | bar: Tue 08 to Fri 11; Mon 14 to Fri 18; Mon 21 to Tue 22
2 | Data Enrichment | 09-Apr | 10-Apr | 1 | bar: Tue 08 to Fri 11; Mon 14 to Fri 18; Mon 21 to Tue 22
3 | Analysis Planning | 10-Apr | 11-Apr | 1 | bar: Tue 08 to Fri 11; Mon 14 to Fri 18; Mon 21 to Tue 22
4 | Data Exploration | 11-Apr | 13-Apr | 2 | bar: Tue 08 to Sat 12; Mon 14 to Fri 18; Mon 21 to Tue 22
5 | Data Cleaning | 12-Apr | 14-Apr | 2 | bar: Tue 08 to Fri 18; Mon 21 to Tue 22
6 | Feature Engineering | 14-Apr | 16-Apr | 2 | bar: Tue 08 to Fri 11; Mon 14 to Fri 18; Mon 21 to Tue 22
7 | SQL Development | 15-Apr | 17-Apr | 2 | bar: Tue 08 to Fri 11; Mon 14 to Fri 18; Mon 21 to Tue 22
8 | Data Processing | 16-Apr | 18-Apr | 2 | bar: Tue 08 to Fri 11; Mon 14 to Fri 18; Mon 21 to Tue 22
9 | Data Visualization | 17-Apr | 19-Apr | 2 | bar: Tue 08 to Fri 11; Mon 14 to Fri 18; Mon 21 to Tue 22
10 | Insights Generation | 18-Apr | 20-Apr | 2 | bar: Tue 08 to Fri 11; Mon 14 to Sat 19; Mon 21 to Tue 22
11 | Recommendations | 19-Apr | 21-Apr | 2 | bar: Tue 08 to Fri 11; Mon 14 to Tue 22
12 | Power BI Dashboard | 20-Apr | 21-Apr | 1 | bar: Tue 08 to Fri 11; Mon 14 to Fri 18; Sun 20 to Tue 22
13 | Presentation & Submit | 21-Apr | 22-Apr | 1 | bar: Tue 08 to Fri 11; Mon 14 to Fri 18; Mon 21 to Tue 22
■ Active Task |  |  | Weekend